## Slide 1: Third Meeting of the Network for the Coordination of Statistical Training in Asia and Pacific
Progress Report of the Network Work Program
5 December 2017
SIAP, 4th Floor JETRO-IDE Building
Chiba, Japan

## Slide 2: Background:
The Network with SIAP as its Secretariat was established by the ESCAP Committee on Statistics during its third session.
The inception and organizational meeting of the Network was held on 22 to 24 April 2014 in Chiba, Japan.
The Second Meeting of the Network was held on March 4, 2016 to review and update its work-programme, including that of the Sub-group.

## Slide 3: Background:
During the Second Meeting of the Network, discussions and decisions were made on the following:
  Extending its work to other areas of official statistics
  Establishing a database on experts and training resources on official statistics
  Development of a programme for certifying trainers and training institutes on official statistics

## Slide 4: Background:
Also, during the meeting and based on the discussions and decisions made the 2016-17 work programme of the Network was formulated with the following three focus outputs:
  Identified training gaps in understanding, measuring and monitoring SDGs;
  Database of compiled training resources that is accessible to the Network members; and
  Common curriculum for priority statistical training on agricultural and rural statistics

## Slide 5: Output-based Work Programme of the Network for 2016-2017
OUTPUTS | ACTIVITIES | PARTNERS | TIMEFRAME
Identified training gaps in understanding, measuring and monitoring SDGs | Members assess training needs on SDGs at national level SIAP shares good practices on country assessments | SIAP, Philippines, Thailand, Bangladesh, Pakistan, India, Indonesia | Apr–Dec 2016

## Slide 6: Output-based Work Programme of the Network for 2016-2017
2. Database of training resources compiled and accessed by the Network members | Develop a concept note for a prototype for the database design (including specifications of credentials, resource materials) Create a beta version of the database of resources with contribution from the Network members (on SIAP website) A task team reviews existing certification programme (e.g. SESRIC) and formulate recommendations. | Japan, SIAP, India, Malaysia, Philippines, Russia, WBG Team: Malaysia, Bangladesh, Iran, Indonesia, Pakistan | Apr 2016-June 2017 July-Dec 2017 Apr-Dec 2016

## Slide 7: Output-based Work Programme of the Network for 2016-2017
3. Common curriculum for priority statistical training on agricultural and rural statistics (ARS) | Pilot testing of TNA tools Development of training curricula for ARS | FAO, ESCAP, ADB, Lao PDR (pilot country), India, Viet Nam, Iran | April-Dec 2016 Jan-Dec 2017

## Slide 8: Progress to Date on SDGs Training Gaps …
Some initial activities conducted by SIAP related to SDGs:
  Organized two sub-regional workshops, one for South Asia (in India) and the other in Central Asia (in Kazakhstan), in collaboration with ESCAP Statistics Division and PARIS 21.
  Incorporated the identification of the SDGs training gaps in the developed Training Needs Assessment Tool which was pilot tested in Lao PDR and Mongolia. Updates on this will be elaborated later by our Consultant on this area.

## Slide 9: Progress to Date on the Database …
Some initial activities conducted by SIAP related to the creation of the database of training resources:
  Developed a technical concept note on the creation of the database
  With the assistance from the Government of Japan, through the Ministry of Internal Affairs and Communication, an IT company was engaged to develop a prototype. Updates on this on-going work will be elaborated later.

## Slide 10: Progress to Date on the Curriculum …
Some initial activities conducted by SIAP related to the development of the curriculum for priority training in official statistics:
  Developed a training needs assessment (TNA) tool to identify training gaps
  This TNA tool was revised to incorporate the concern on SDGs. As mentioned earlier, a consultant was hired to do the revision on the TNA and pilot testing was conducted in Lao PDR and Mongolia. More on this on the report of the consultant.

## Slide 11: Some Lessons Learned
The targeted outputs were not fully attained as the initial activities conducted by the Secretariat are mostly just to provide the catalysts of the work to be done.
Most of the member countries who volunteered to facilitate the activities for the attainment of the targeted outputs did not participate much in the said activities.
The importance of the coordination and commitment of the member countries of the network has to be emphasized for the efficient delivery of the work programme.